| Date: | 20.3.26 |
| --- | --- |
| Title: | Magna Park Corby – March 2026 Update Note |

This briefing note summarises all known activity, issues, stakeholder engagement and correspondence relating to Magna Park Corby since 1 January 2026.

1. Highways & Kettering Road Mitigation Works

- Technical approvals from North Northamptonshire Council (NNC) have been significantly delayed, slowing progress on the Kettering Road / Weldon Road mitigation works. The council issued the first draft S278 agreement on 6 February, with GLP/Marq returning revised wording on 11 February to resolve minor points.

- Once the agreement is finalised, GLP/Marq Logistics will be able to book Traffic Management (TM) with the council. Construction dates cannot be confirmed until TM is approved, but delivery is anticipated “within the next couple of months”.

- A separate note to Weldon Parish Council (PC) suggests the works are hoped to be delivered in April within an approximate three-week construction window, subject to TM approval. There has been no breach of Condition 27, as the six-month implementation period has not yet begun.

2. HGV Movements Through Weldon & Enforcement

- Weldon PC has repeatedly raised concerns about HGVs travelling through the village despite the weight restriction, citing examples including Amazon vehicles ignoring signage.

- Councillors have requested additional signage—for example, “No access to MPC” and further 7.5-tonne restriction signs. GLP is reviewing feasibility, noting that any new signage may need to progress through S278 or S106 routes.

- GLP is working with TPA on new on-plot directional signage to guide HGVs away from Weldon and towards the A43.

- A meeting between Gwyn and Weldon PC is planned after the March CLG to address these ongoing concerns.

3. Planning Application NC/24/00392/OUT (Remaining MPC Phases)

- The outline application for the remaining phases, submitted on 2 December 2024, remains undetermined more than 12 months later. GLP escalated the delays to the Leader of NNC on 4 February.

- Officers had previously indicated the application could be delegated for approval subject to the S106 and conditions, but progress on the S106 has been slow—taking five months to receive a first draft despite relevant precedents.

- The delays are preventing delivery of significant economic and employment benefits associated with 4.5 million sq ft of logistics development.

4. Political Engagement & Stakeholder Relations

- Early-year engagement has continued with Cllr Eddie McDonald, including calls to discuss progress and ongoing concerns.

- Regular updates are being exchanged on HGV movements, enforcement interpretation and site activity.

- GLP has escalated planning delays to senior political leadership, highlighting the economic impact of continued inaction.

5. Operations & Site Updates (Nike / MPC4a)

- MPC4a fit-out works are now being delivered by Glencar on behalf of Nike. TSL no longer has any active presence on site.

- Nike’s operational programme is substantially delayed, with the earliest go-live date now projected for late 2027.

- These delays may influence stakeholder perceptions of site momentum and should be acknowledged in forthcoming CLG discussions.

6. GLP / Marq Logistics Brand Transition

- The brand transition from GLP to Marq Logistics is underway and should be referenced consistently in external communications.